## Costed BOM
Category	AO Part #	Description	Manufacturer	Manufacturer PN	Distributor	Distributor SKU	Qty Per	UOM	Price Per Unit	Price Total	Qty to Order	PO	PO Date	Receiving ETA	Actual	Comment	Lead weeks	Notes	Mini, per unit
										$1,012.97	1000				Receiving

Hardware	HD-MS0054	Square Bumper			Advanced Antivibration components	V10R87-B08130	8	ea	$0.087	$0.70	8000	PO04165	08/28/14		9800 rec'vd	17 sheets in stock, rest backordered 5-6 weeks	1	8/19 They'll email with leadtimes. Ordering 12,000 to cover Mini too.	4

Firmware		Firmware, Marlin 2014Q4			Aleph Objects		1	ea			1000						0
Printed	PP-GP0083	bed_finger			Aleph Objects		4	ea	$0.100	$0.40	4000						4
Printed	PP-GP0084	double_bearing_holder			Aleph Objects		3	ea	$2.890	$8.67	3000						4
Printed	PP-GP0117	Bearing Holder v1.1b, TAZ			Aleph Objects		5	ea	$1.170	$5.85	5000						4
Printed	PP-GP0086	Belt clamp, TAZ			Aleph Objects		2	ea	$0.080	$0.16	2000						4
Printed	PP-GP0089	LCD_spacer			Aleph Objects		4	ea	$0.005	$0.02	4000						4
Printed	PP-GP0120	feed_tube_holder_v2.0			Aleph Objects		1	ea	$0.660	$0.66	1000						4
Printed	PP-GP0074	feed_tube spinner			Aleph Objects		1	ea	$0.530	$0.53	1000						4
Printed	PP-GP0061	herringbone_large_gear			Aleph Objects		1	ea	$2.430	$2.43	1000						4
Printed	PP-GP0062	herringbone_small_gear			Aleph Objects		1	ea	$0.340	$0.34	1000						4
Printed	PP-GP0060	Wade Reloaded Bearing Washer			Aleph Objects		1	ea	$0.020	$0.02	1000						4
Printed	PP-GP0058	Wade Reloaded Extruder Block			Aleph Objects		1	ea	$4.010	$4.01	1000						4
Printed	PP-GP0059	Wade Reloaded Idler Block			Aleph Objects		1	ea	$0.900	$0.90	1000						4
Printed	PP-GP0091	extruder_latch			Aleph Objects		1	ea	$0.260	$0.26	1000						4
Printed	PP-GP0151	X Idler v2.3 , TAZ			Aleph Objects		1	ea	$2.770	$2.77	1000						4
Printed	PP-GP0128	X Carriage v2.0 ,TAZ			Aleph Objects		1	ea	$6.000	$6.00	1000						4
Printed	PP-GP0094	x_carriage_guide			Aleph Objects		1	ea	$0.760	$0.76	1000						4
Printed	PP-GP0152	X Motor Mount v2.1, TAZ			Aleph Objects		1	ea	$2.820	$2.82	1000						4
Printed	PP-GP0096	Extruder mount, TAZ			Aleph Objects		1	ea	$6.510	$6.51	1000						4
Printed	PP-GP0150	y_belt_mount			Aleph Objects		1	ea	$2.460	$2.46	1000						4
Printed	PP-GP0121	Y Mount Chassis v2.1, TAZ			Aleph Objects		4	ea	$0.730	$2.92	4000						4
Printed	PP-GP0122	y_mount_table-2.1			Aleph Objects		4	ea	$0.730	$2.92	4000						4
Printed	PP-GP0123	Z Top Drive v1.2-Left, TAZ			Aleph Objects		1	ea	$3.560	$3.56	1000						4
Printed	PP-GP0124	Z Top Drive v1.2-Right, TAZ			Aleph Objects		1	ea	$3.560	$3.56	1000						4
Printed	PP-GP0125	Z Motor Mount v2.1 nonswitch-Right			Aleph Objects		1	ea	$5.840	$5.84	1000						4
Printed	PP-GP0126	Z Motor Mount v2.1 switch-Left , TAZ			Aleph Objects		1	ea	$6.070	$6.07	1000						4
Printed	PP-GP0109	Spool Arm, TAZ			Aleph Objects		1	ea	$2.010	$2.01	1000						4
Printed	PP-GP0118	Bed Corner v2.5			Aleph Objects		4	ea	$0.250	$1.00	4000						4
Printed	PP-GP0107	shipping_clamp_a			Aleph Objects		4	ea	$0.250	$1.00	4000						4
Printed	PP-GP0108	shipping_clamp_b			Aleph Objects		4	ea	$0.210	$0.84	4000						4
Printed	PP-GP0113	Y Corner Left v1.2, TAZ			Aleph Objects		2	ea	$2.010	$4.02	2000						4
Printed	PP-GP0114	Y Corner Right v1.2, TAZ			Aleph Objects		2	ea	$2.010	$4.02	2000						4
Printed	PP-GP0115	Y Bearing Mount v2.6.b, TAZ			Aleph Objects		1	ea	$0.970	$0.97	1000						4
Printed	PP-GP0116	Y Motor Mount v2.4, TAZ			Aleph Objects		1	ea	$5.170	$5.17	1000						4
Printed	PP-GP0127	Z Nut Mount V 2.0 , TAZ			Aleph Objects		2	ea	$2.050	$4.10	2000						4
Printed	PP-GP0154	Electronics Case Mount v1.0			Aleph Objects		4	ea	$0.240	$0.96	4000						4
Printed	PP-GP0153	Extruder Fan Mount v1.0, TAZ			Aleph Objects		1	ea	$1.120	$1.12	1000						4
Printed	PP-GP0163	Long Shim			Aleph Objects		2	ea	$1.000	$2.00	2000
Accessories	RM-AB0079	ABS 3mm, 1m filament sample, LulzBot green			Aleph Objects		1	ea	$0.200	$0.20	1000
Mechanical	HE-SH0016	Assy, Budaschnozzle 2.0c with 0.35 nozzle			Aleph Objects		1	ea	$52.000	$52.00	1000

Electronic	EL-MS0126	CONN PLUG, 25 POS, IDC GOLD	3M	8325-8000	AA ADAM ELECTRONIC TECHNOLOGY CO., LTD (AMICU ELECTRONICS)		1	ea	$0.540	$0.54	1000	PO04237	07/24/14		1000-09/18	Paid 8/27		Digikey	3M15408-ND	$4.80	Currently 157 IS/5 wk LT
Electronic	EL-MS0127	CONN D-SUB RCPT 25 POS IDC GOLD	3M	8325-8003	AA ADAM ELECTRONIC TECHNOLOGY CO., LTD (AMICU ELECTRONICS)		1	ea	$0.340	$0.34	1000	PO04237	07/24/14		1000-09/18	Paid 8/27		Digikey	3M15414-ND	$5.45	44 IS/ 12 wk LT

Mechanical	HD-MS0002-3	Borosilicate Glass Bed 300mm x 300mm			Allen Scientific		1	ea	$12.850	$12.85	1000	PO04166	08/27/14		1056 rec'vd	Lead time is 9-25. PO Sent for 1020 sheets.	4	RFQ sent 8/19	1 of 170mm x 170mm

Hardware	HD-MS0027	Spring, Extruder, 6mm OD, 0.8mm WD, 9.7mm FL			Associated Spring	C0240-032-0380-M	6	ea	$0.137	$0.82	6000	PO04167	09/05/14	09/19/14	6100 rec'vd		2	The other TAZ spring is from AS too. (UPS Tracking shows we received these 9/15/2014 – TS 9/26/2014) 4000 units shipping 10/13/2014 – TS	2?

Mechanical	HD-BL0009	GT2, Single sided Neoprene Belt, 2mm pitch, 582 teeth, 6mm wide,fiberglass cords			B & B Manufacturing, Inc	1164-2P-06 (2MR-1164-06)	2	ea	$2.850	$5.70	2000	PO04168	08/28/14	11/07/14	2040 rec'vd		7		2 different length
Mechanical	HD-MS0033	GT2 Timing Pulley, 5mm Bore Aluminum			B & B Manufacturing, Inc	16-2P06M6CA5 5MM BORE ALUMINUM	2	ea	$3.250	$6.50	2000	PO04168	08/28/14	See Notes	2040 rec'vd		1	Delivery: 500 Stock, Balance 8-10 Weeks	2

Tools	TL-HD0048	Elmer's X-Acto No. 1 Precision Knife – Aluminum		X3201	Utrecht Art Supplies	UNI-EPIX3001	1	ea	$1.940	$1.94	1030	PO04344	09/02/14	10/09/14	1063 rec'vd	Paid 9/2 – Delivery on or before 10/9/2014		http://www.business-supply.com/p-8487-elmers-x-acto-no-1-precision-knife-aluminum.aspx?utm_le=true&id={adwords_producttargetid}&gclid=CJXMiLXrqbcCFao-Mgod8hkAkQ

Tools	TL-HD0050	6" Professional Long Nose Pliers			Newark	43W8049	1	ea	$5.180	$5.18	1000	PO04355	09/04/14	10/06/14	1010 rec'vd		2

Mechanical	PP-FP0012	frame_connector			Custom Laser Design		7	ea	$2.450	$17.15	7000	PO04173	08/28/14	See Notes	2550	Weekly Shipments	3	912 upper plates shipping 10/6 and the remainer will ship Fri. 10/10 – TS
Mechanical	PP-FP0011	TAZ name plate, laser cut			Custom Laser Design		1	ea	$3.700	$3.70	1000	PO04173	08/28/14	See Notes	680	Weekly Shipments	3	1008 lower plates shipping 10/6/2014 remainder shipping 10/10 – TS

Hardware	HD-MS0061	KNOB CLR/MATTE .50"DIA 6MM SHAFT		OEJA-50-3-7	Digikey	226-3128-ND	1	ea	$3.170	$3.17	1000	PO04398	09/12/14	See Notes	1025 rec'vd		1	875 units available / Bal Est 7 Weeks ETA 10/31 – TS
Electronic	EL-MS0141	Term Ring Non Ins 26-22AWG #4	Panduit	P22-4R-M	Helind	298-10067-ND	3	ea	$0.087	$0.10	3000	PO04424	09/12/14	09/192014	3100-09/18	Available
Electronic	PC-CN0010	IDC 10POS Dual 30AU	FCI	BRG71600-010LF	Helind	609-1739-ND	2	ea	$0.550	$1.10	2000	PO04424	09/12/14	09/19/14	2108-09/18	In Stock
Electronic	EL-MS0134	Backshell DB25 Flat Ribbon	Norcomp, Inc.	976-025-010R031	Digikey	976-25RPE-ND	1	ea	$1.125	$1.13	1000	PO04398	09/12/14	See Notes	437-09/18	400 O/H 09/15-488 B/O		437 Available for 9/19/2014 / Bal Est 9 weeks ETA 11/6/2014 – TS / 588 Shipped 10/16/2014-TS
Electronic	EL-MS0133	14-POS, panel mount w. brass inserts	TE	211103-1	Digikey	A106308-ND	4	ea	$3.771	$15.08	4000	PO04398	09/12/14	10/07/14	3622 rec'vd?	2 WK LT		1884 Units ETA 9/30/2014 – Remaining 1200 ETA 10/7/2014
Electronic	EL-MS0128	4-POS, free hanging	TE	206429-1	Digikey	A1357-ND	1	ea	$2.552	$2.55	1000	PO04398	09/12/14	09/19/14	1100-09/18
Electronic	EL-MS0131	14-POS, free hanging	TE	206044-1	Digikey	A1358-ND	3	ea	$2.403	$7.21	3000	PO04398	09/12/14	09/19/14	3100-09/18
Electronic	PC-CN0035	4-POS, panel mount w. brass inserts	TE	211102-01	Helind	A25053-ND	1	ea	$3.010	$3.01	1000	PO04424	09/12/14	09/19/14	1100-09/18	Available
Electronic	EL-MS0142	CONN RECEPT FASTON 22-26AWG .110		7-520365-2	TTI	7-520365-2	6	ea	$0.109	$0.65	6000	PO04428	09/15/14	09/19/14	6000 rec'vd	21000 units shipping asap / Balance has a 6 week lead but they are trying to expedite.
Electronic	EL-MS0143	Conn Fast Receptacle14-16 AWG .250		3-350820-2	TTI	3-350820-2	2	ea	$0.077	$0.15	2000	PO04428	09/15/14	09/19/14	2000-9/23
Electronic	EL-MS0123	20-24 AWG Tin Pin for Plug	TE	1-66106-5	Digikey	A31991TR-ND	35	ea	$0.200	$7.00	35000	PO04398	09/19/14	09/24/14	60000	Do not need more for Juniper	12+ WK LT	There was a 12 week lead on PN-A31991TR-ND / Ordered 4k of alternate PN-A032008-TR-ND Under PO 04547. B/O of PO03450 from June for 20,000 ETA 10/13.
Electronic	EL-MS0124	20-24 AWG Tin Sockets for Receptacle	TE	1-66331-4	Digikey	A31995TR-ND	46	ea	$0.230	$10.58	46000	PO04398	09/12/14	See Notes	46000-09/18			Received 40K under correct part number A31995TR-ND / and 4K reel under unacceptable alternate PN A31987TR-ND – TS (Mary, before I exchange these / For the correct part, please advise if we need to have the additional units or do we have enough in stock to cover the 46K units needed?)
Electronic	EL-MS0121	14-18 AWG Tin Sockets for Receptacle	TE	1-66358-6	Helind	A31997TR-ND	3	ea	$0.193	$0.58	3000	PO04424	09/12/14	09/19/14	4000-09/19	4000 pc reel / Available
Electronic	EL-MS0122	14-18 AWG Tin Pin for Plug	TE	1-66359-4	Helind	A31998TR-ND	3	ea	$0.174	$0.52	3000	PO04424	09/12/14	09/19/14	4000-9/18	4000 pc reel / Available
Electronic	EL-MS0129	Cable Clamp for 14-Pos; 0.453” opening	TE	206070-8	Helind	A32516-ND	2	ea	$1.920	$3.84	2000	PO04424	09/12/14	09/19/14	2100-09/18	Available
Electronic	EL-MS0130	Cable Clamp for 14-Pos; 0.453” opening; full cover	TE	AMP1546349-2	Helind	A33754-ND	1	ea	$3.390	$3.39	1000	PO04424	09/12/14	09/19/14	1100-09/18	Available
Electronic	EL-WR0104	24AWG Stranded – Orange		C2015A.21.04	Digikey	C2015A-1000-ND	2520	mm	$0.000	$0.64	2520000	PO04398	09/12/14	09/19/14	3000 rec'vd	Have 7X1000FT Need 9X1000FT – MKE
Electronic	EL-WR0105	24AWG Stranded – Black		C2015A.21.01	Digikey	C2015B-1000-ND	3560	mm	$0.000	$0.91	3560000	PO04398	09/12/14	09/14/14	14x1000FT-09/18	Available
Electronic	EL-WR0111	24AWG Stranded – Blue		C2015A.21.07	Digikey	C2015L-1000-ND	690	mm	$0.000	$0.18	690000	PO04398	09/12/14	09/19/14	2x1000FT-09/18	Available
Electronic	EL-WR0103	24AWG Stranded – Red		C2015A.21.03	Digikey	C2015R-1000-ND	4800	mm	$0.000	$1.23	4800000	PO04398	09/12/14	09/14/14	10x1000FT	Have 5X1000FT Need 15X1000FT – MKE
Electronic	EL-WR0107	24AWG Stranded – White		C2015A.21.02	Digikey	C2015W-1000-ND	1160	mm	$0.000	$0.30	1160000	PO04398	09/12/14	09/14/14	4x1000FT-09/18	Available
Electronic	EL-WR0109	24AWG Stranded – Yellow		C2015A.21.05	Digikey	C2015Y-1000-ND	1100	mm	$0.000	$0.28	1100000	PO04398	09/12/14	09/14/14	4x1000FT-09/18	Available
Electronic	EL-WR0106	16AWG Stranded – Red		C2065A.21.03	Digikey	C2065R-1000-ND	650	mm	$0.001	$0.45	650000	PO04398	09/12/14	09/19/14	3x1000FT-09/18	Available
Electronic	EL-WR0108	16AWG Stranded – Violet		C2065A.21.19	Digikey	C2065V-1000-ND	1200	mm	$0.001	$0.74	1200000	PO04398	09/12/14	09/14/14	1x1000 rec'vd	3X1000 B/O		1 shipping / 3 on BO
Electronic	EL-WR0110	16AWG Stranded – Yellow		C2065A.12.05	Digikey	C2065Y-100-ND	50	mm	$0.001	$0.06	50000	PO04398	09/12/14	09/14/14	5x1000 ft	Available
Electronic	EL-SW0020	SWITCH ROCKER DPST 20A 125V	E-switch	R5ABLKBLKFF0	Helind	EG1529-ND	1	ea	$0.860	$0.86	1000	PO04424	09/12/14	09/19/14	1100-09/18
Electronic	EL-WR0098	25Cond Ribbon LT GRY		HF365/25SF	Digikey	MD25R-100-ND	160	mm	$0.003	$0.48	160000	PO04398	09/12/14	09/14/14	200FT-09/18	Available
Electronic	EL-SW0021	Switch SIM Roll SPDT 3A 125V	Omron	SG-3GL13PT	Digikey	SW768-ND	3	ea	$0.609	$1.83	3000	PO04398	09/12/14	09/14/14	3100-09/18	Available
Electronic	EL-WR0099	Shielded 4Cond 22AWG		0762A.41.10	Digikey	W504-1000-ND	3657	mm	$0.001	$3.72	3657000	PO04398	09/12/14	09/19/14	500FT-09/18	Available
Electronic	EL-MS0059	CONN TERM FEMALE 22-24AWG TIN	Molex Inc.	16-02-0102	Digikey	WM2510-ND	92	ea	$0.030	$2.76	92000	PO04398	09/12/14	09/19/14	92000 rec'vd	Available
Electronic	EL-MS0205	CONN TERM MALE 22-24AWG TIN	Molex	16-02-0107	Digikey	WM2517TR-ND	32	ea	$0.042	$1.34	32000	PO04398	09/12/14	09/19/14	32100-09/18	2 WK LT
Electronic	EL-MS0075	8-POS .100 Dual (Black)			TTI	WM2521-ND	1	ea	$0.400	$0.40	1000	PO04428	09/11/14	09/26/14	1100-9/23
Electronic	EL-MS0074	20-POS .100 Dual (Black)			TTI	WM2527-ND	1	ea	$0.600	$0.60	1000	PO04428	09/11/14	09/26/14	1100 rec'vd
Electronic	PP-MP0059	CONN HOUSING MALE 2POS .100			TTI	WM2533-ND	4	ea	$0.124	$0.50	4000	PO04428	09/11/14	09/26/14	4100-9/23
Electronic	EL-MS0061	Connector, 4 pin Male housing with latch	Molex	701070003	Helind	WM2535-ND	5	ea	$0.130	$0.65	5000	PO04424	09/12/14	09/19/14	5100-09/18
Electronic	PC-CN0001	CONN HOUSING 2POS .100 W/LATCH			TTI	WM2900-ND	10	ea	$0.062	$0.62	10000	PO04428	09/11/14	09/26/14	16500 rec'vd
Electronic	PC-CN0003	Connector Housing 3POS .100 W/Latch			TTI	WM2901-ND	3	ea	$0.060	$0.18	3000	PO04428	09/11/14	09/26/14	3000-9/23
Electronic	EL-MS0062	Connector, 4 pin Female housing with latch	Molex	50579404	Helind	WM2902-ND	12	ea	$0.062	$0.74	12000	PO04424	09/12/14	09/19/14	12000-09/18
Electronic	PC-CN0032	Term Block Plug 2POS STR 5.08MM			TTI	WM7819-ND	5	ea	$0.456	$2.28	5000	PO04428	09/11/14	09/26/14	5000 rec'vd
Electronic	PC-CN0036	Term Block Plug 6POS STR 5.08MM		20000	Helind	WM7822-ND	1	ea	$1.340	$1.34	1000	PO04424	09/12/14	09/19/14	1100-09/18
Helind	EL-MS0140	Cable Clamp for 4-Pos; 0.329” opening	TE	1-206062-5	Helind	A104910-ND	1	ea	$1.420	$1.42	1000	PO04424	09/12/14	09/19/14	1100-09/18	In Stock

Mechanical	PP-FP0029	Cover, Electronics, Guava			EPOCS		1	ea	$5.500	$5.50	1030	PO04174	09/15/14	10/13/14			4
Mechanical	PP-FP0030	Enclosure, Sheet Metal, Guava			EPOCS		1	ea	$23.750	$23.75	1030	PO04174	09/15/14	10/13/14			4
Mechanical	PP-FP0009	LCD cover back, black anodized			EPOCS		1	ea	$13.750	$13.75	1030	PO04174	09/15/14	10/13/14			4
Mechanical	PP-FP0008	LCD cover front, black anodized			EPOCS		1	ea	$3.250	$3.25	1030	PO04174	09/15/14	10/13/14			4
Mechanical	PP-MP0045	Bed Mount Plate, Aluminum			EPOCS		1	ea	$16.500	$16.50	1030	PO04174	09/15/14	10/13/14			3
Mechanical	PP-FP0015	Y Axis End Idler			EPOCS		1	ea	$6.500	$6.50	1030	PO04174	09/15/14	10/13/14
Mechanical	PP-FP0016	Y Axis End Motor			EPOCS		1	ea	$6.350	$6.35	1030	PO04174	09/15/14	10/13/14
Mechanical	PP-FP0031	X end Plate			EPOCS		2	ea	$11.500	$23.00	2060	PO04174	09/15/14	10/13/14

Consumable	TL-CS0003	ArmsKeeper Glues: Maxi-Cure Extra Thick			FPR Games	ARM05113	1	g	$0.141	$0.14	1000

Tools	TL-MS0020	Stainless Steel/Straight Instrument Cleaner Brush			Gordon Brush	906501	1	ea	$5.290	$5.29	1000	PO04369	09/05/14	09/12/14	84 rec'vd	These are sold in packs of 12	3	Shipped 9/5/2014 http://www.gordonbrush.com/stainless-steel/straight-instrument-cleaner-brush-p-1294-l-en.html

Tools	TL-HD0047	Tekton 13-pc. Long Arm Ball Hex Key Wrench Set (Metric)			Boston Industrial Tools	25220	1	ea	$4.990	$4.99	1000	PO04353	09/04/14	10/03/14	1010 rec'vd		3

Consumable	TL-CS0099	Hot Glue			Hobby Lobby		1	g	$0.000	$0.00	1000

Consumable	TL-CS0010/TL-CS0114	Lithium Grease			Home Depot/Amazon	934178	3	g	$0.020	$0.06	3000

Mechanical	HD-BU0001	DryLin® R - Solid polymer bearing RJM-01, 10mm			IGUS	RJM-01-10	11	ea	$1.680	$18.48	11000	PO04176	08/28/14		5000 rec'vd	6330 B/O – ETA 10/13 (11/24/2014 Emailed Rep to get an ETA on the back ordered 6330 units.)	2	See Desen Weier Quote; Freight charges amortized

Electronic	EL-FA0011	FAN,24VDC,Sleeve,5.75CFM,40X40X10MM,60mA 6000RPM,1.44W,280MM LEADS,CE/RoHS			Kysan	TF4010-24H-S	1	ea	$1.550	$1.55	1000	PO04177	08/28/14		1050-10/02	“Lead time is about 5-6 weeks.”
Electronic	EL-FA0012	FAN,24VDC,BALL,31.60CFM,80×80×15 MM,100mA			Kysan	TF8015-24M-B	1	ea	$2.450	$2.45	1000	PO04177	08/28/14		1050-10/02	“Lead time is about 5-6 weeks.”

Documentation	DC-MN0010	Lulzbot-Taz 4.1 User Manual			Lightning Source		1	ea	$3.530	$3.53	1000	PO04652/04682	10/07/14	200 10/13/14	Good	200 will arrive on 10/13 the rest arrive by 10/20

Accessories	DC-LB0026	Label, Taz 3D printer barcode			Lightspeed Color		1	ea	$0.143	$0.14	1000	PO04683	10/07/14	10/10/14	Good
Accessories	DC-LB0007	Label, Top of Box			Lightspeed Color		1	ea	$0.238	$0.24	1000	PO04683	10/07/14	10/10/14	Good
Accessories	DC-LB0024	Label, Bottom of Box			Lightspeed Color		1	ea	$0.238	$0.24	1000	PO04683	10/07/14	10/10/14	Good
Accessories	DC-LB0025	TAZ v4.1 serial number sticker			Lightspeed Color		2	ea	$0.029	$0.06	2000	PO04683	10/07/14	10/10/14	Good
Documentation	DC-MS0023	Test/Acceptance record TAZ 4.1			Lightspeed Color		1	ea	$0.476	$0.48	1000	PO04683	10/07/14	10/10/14	Good
Documentation	DC-MS0024	Quality checklist, TAZ 4.1			Lightspeed Color		1	ea	$0.762	$0.76	1000	PO04683	10/07/14	10/10/14	Good
Documentation	DC-MS0025	Packing List, TAZ 4.1			Lightspeed Color		1	ea	$0.238	$0.24	1000	PO04683	10/07/14	10/10/14	Good
Documentation	DC-MN0011	Getting Started Guide, TAZ 4			Lightspeed Color		1	ea	$1.619	$1.62	1000	PO04683	10/07/14	10/10/14	Good

Mechanical	HD-RD0004	8mm Smooth Rod x 18-19mm			MBK		1	ea	$4.730	$4.73	1000	PO04178	09/15/14	10/05/14	2500 rec'vd	quote requested on 9/11	2	(970) 532-3878
Hardware	HD-BT0108	Hobbed Bolt, M8 x 50mm Hex head, 26mm offset, Stainless Steel			Quatro		1	ea	$5.850	$5.85	1000	PO04550	09/19/14	See Notes	Seth	Toni getting quote from Quatro		1250 units due 10/10/2014 remaining 1250 by 11/3/2014

Hardware	HD-TB0007	Feed Tube, PTFE			McMaster-Carr Supply Company	5239K12	850	mm	$0.006	$4.71	850000	PO04521	09/18/14	10/03/14	56 feet rec'vd		1
Tools	TL-HD0014	Standard-Head Open-End Wrench Black Finish, 13mm Sz, 4-7/8" Length, 15 Deg Angle			McMaster-Carr Supply Company	5488A19	1	ea	$7.660	$7.66	1000	PO04521	09/18/14	10/03/14	1020 rec'vd			http://www.lowes.com/pd_337643-25428-85661_0__?productId=3387150&Ntt=13mm+wrench&Ns=p_product_price|0
Tools	TL-HD0008	Stainless Steel Pocket Rule Semiflexible, Metric Grads, 150 mm Length			McMaster-Carr Supply Company	6813a62	1	ea	$2.620	$2.62	1000	PO04521	09/18/14	10/03/14	1120 rec'vd
Electronic	EL-MS0073	Tubing, Corrugated Loom .25"	Panduit	CLT25F-C20	Fastenal	708161	2320	mm	$0.000	$0.01	2320000	PO04498	09/17/14	09/26/14	8100FT-9/22	Have 41X100FT on Hand as of 09/12-MKE
Electronic	EL-MS0139	Tubing, Corrugated Loom .375"	Panduit		McMaster-Carr Supply Company	7840K32	300	mm	$0.001	$0.37	300000	PO04551	09/19/14	09/22/14	18 feet
Electronic	TL-CS0083	EMI/RFI-Shield Heat-Shrink Tubing 3/16" ID Before, 3/32" ID After, 48" L, Black			McMaster-Carr Supply Company	7937K31	230	mm	$0.015	$3.38	230000	PO04967	10/17/14	See Notes	20X4' rec'vd	47X4Feet O/H – 09/17 – MKE		Allcable – Shipping 100 units immediately, balance to ship on or before 11/3
Electronic	TL-CS0129	Interference-Shielding Heat-Shrink Tubing, 3/8" ID Before, 3/16" ID After, 48" Long, Black			McMaster-Carr Supply Company	7937K33	175	mm	$0.027	$4.66	175000	PO04967	10/17/14	See Notes	162' rec'vd	QTY?		Allcable – Shipping 130 units immediately, balance to ship on or before 11/3
Hardware	HD-MS0197	Type 316 Stainless Steel Socket Head Cap Screw, M5 Thread, 12mm Length, .8mm Pitch			Timberline	DMS-08350030	1	ea	$0.062	$0.06	1000	PO04552	09/19/14	09/30/14	1000 rec'vd	3 WK LT	1	McMaster Carr 92290A228
Hardware	HD-MS0164	Aluminum Male-Female Threaded Hex Standoff, 3/16" Hex, 3/16" Length			McMaster-Carr Supply Company	93505A853, 4-40	2	ea	$0.660	$1.32	2000	PO04521	09/18/14	09/22/14	2000-9/23
Hardware	HD-WA0027	Metric 18-8 Stainless Steel Internal-Tooth Lock Washer, M3 Screw Size, 6mm OD, .4mm min Thick		WF6330000/	Fastenal	W504-1000-ND	2	ea	$0.006	$0.01	2000	PO04498	17-Sep	09/26/14	2000-9/22		1
Hardware	HD-MS0157	Plastic Head Thumb Screw, Knurled Head, M5 Thread, 0.8mm Pitch, 20mm Long			McMaster-Carr Supply Company	96016A245	1	ea	$0.738	$0.74	1000	PO04521	09/18/14	10/03/14	1000 rec'vd
Hardware	HD-MS0203	Steel Compression Spring, Zinc-Plated Music Wire, 1.00" Long,.300" OD,.022" Wire			Associated Spring	CO300-022-1000-M	1	ea	$0.271	$0.27	1000	PO04167	09/05/14	09/10/14	1100 rec'vd		2	This replaces McMaster PN 9657K301
Electronic	EL-MS0160	Noninsulated Wire Ferrule, 14 AWG, .39" Pin Length			McMaster-Carr Supply Company	9681K25	1	ea	$0.064	$0.06	1000	PO04521	09/18/14	09/22/14	1100-9/23

Hardware	HD-NT0017	T-nut M5 Thread			Misumi	HNKK5-5	77	ea	$0.092	$7.05	77000	PO04164	08/21/14	First ship date 09/22	770 rec'vd		2
Mechanical	HD-RD0018	10mm x 500mm smooth rod			Misumi	SSFHR10-500	6	ea	$13.230	$79.38	6000	PO04164	08/21/14	First ship date 09/22	6000 rec'vd		1
Mechanical	HD-MS0194	Coupling, Set Screw, Misumi GSASL16-5-5			Misumi	GSASL16-5-5	2	ea	$7.500	$15.00	2000	PO04164	08/21/14	First ship date 09/22	800 rec'vd
Mechanical	HD-EX0010	Aluminum Frame, extrusion 20mm x 20mm x 500mm, black			Misumi	HFSB5-2020-500	4	ea	$4.150	$16.60	4000	PO04164	08/21/14	First ship date 09/22	4000 rec'vd		4
Mechanical	HD-EX0011	Aluminum Frame LTP, extrusion 20mm x 20mm x 500mm,Tapped M5x0.8 on one End, black			Misumi	HFSB5-2020-500-LTP	4	ea	$5.840	$23.36	4000	PO04164	08/21/14	First ship date 09/22	4000 rec'vd		4
Mechanical	HD-EX0012	Aluminum Frame TPW, extrusion 20mm x 20mm x 500mm,Tapped M5x0.8 on both Ends, black			Misumi	HFSB5-2020-500-TPW	2	ea	$7.420	$14.84	2000	PO04164	08/21/14	First ship date 09/22	2000 rec'vd		4
Mechanical	HD-MS0172	Screw, Lead, Misumi MTSBRK12-420-F7-R8-T9-Q8-S20-E5-FE0-FW7-FY1			Misumi	MTSBRK12-420-F7-R8-T9-Q8-S20-E5-FE0-FW7-FY1	2	ea	$24.180	$48.36	2000	PO04164	08/21/14	First ship date 09/22	610 rec'vd
Mechanical	HD-MS0173	Nut, Lead Screw, Resin, Misumi MTSRR12			Misumi	MTSRR12	2	ea	$7.400	$14.80	2000	PO04164	08/21/14	First ship date 09/22	610 – rec'vd

Electronic	EL-CA0001	6ft USB 2.0 A Male to B Male 28/24AWG Cable			Monoprice	5438	1	ea	$1.090	$1.09	1000	PO04209	10/6/14	10/13/14	1050 rec'vd

Electronic	EL-MS0008	Heavy Duty Power Connectors HOUSING ONLY, BLACK POWERPOLE 15/45			Mouser	879-1327G6-BK	2	ea	$0.184	$0.37	2000	PO04556	09/19/14	09/26/14	2000 rec'vd
Electronic	EL-MS0010	Heavy Duty Power Connectors POWERPOLE 15A CONT			Mouser	879-1332-BK	2	ea	$0.121	$0.24	2000	PO04556	09/19/14	09/26/14	2000-9/23
Electronic	EL-CA0016	Flat Cables .050" 10C Shielded Black 28AWG Stranded			Mouser	517-3517/10	685	mm	$0.016	$11.24	685000	PO04556	09/19/14	09/26/14	36FT-9/23

Electronics	PC-BD0027	Silicon Heater, 24V ,360W, 298mm x 298mm, Self Adhesive, w/ connectors			National Plastic Heater		1	ea	$37.900	$37.90	1000	PO04210	08/29/14	See notes	250	750 on B/O	4	250 units to be rcvd by 10/3 + 250 by 10/17 and the remaining units to come by 11/7.

Electronic	TL-HD0178	MOLEX 19069-0117 TERMINAL, RING TONGUE, #10, CRIMP			TTI	55H3650	1	ea	$0.051	$0.05	1000	PO04572	09/23/14	09/30/14	2000 rec'vd			I am trying to go through TTI – Newark is BO till 10/18
Electronic	EL-WR0013	HOOK-UP WIRE 100FT 18AWG TIN-COPPER BLK, C2064A.12.01			Newark Electronic	78R8041	240	mm	$0.001	$0.24	240000	PO04570	09/23/14	10/01/14	800 feet

Hardware	EL-MS0144	Connector Accessories, Sealing Cap, Shell Size 17			Onlinecomponents.com	207445-3	1	ea	$1.980	$1.98	1000	PO04589	09/24/14	10/01/14	1000 rec'vd			http://www.onlinecomponents.com/te-connectivity-amp-brand-2074453.html?p=10316937

Consumable	OF-CS0023	Office Depot® Brand Cleaning Duster, 10 Oz.			Office Depot	110284	0.04	ea	$4.665	$0.19	40					7pkg of 6 cans. Should be on Mfg BoM

Mechanical	HD-MS0206	3M Polyester Tape Green, 50.4 in x 72 yd 3.2 mil, 1 roll per case Bulk		0051115647239	Pack-N-Tape		78	mm	$0.518	$0.52	1 roll	PO 04362	09/05/14				4	I don't know if we need more of this

Electronic	EL-PS0022	Power Supply, 24V, 16.66A, 400W, 4pin, Pengchu Ltd. V2			Pengchu Ltd.		1	ea	$48.000	$48.00	1000	PO04211	08/28/14		588 rec'vd	Slow boat.		When PO04211 was created this line was EL-PS0018, It should have been EL-PS0022
Electronic	KT-EL0026				Pengchu Ltd.		1	ea	$0.000	0	1000	PO04211	08/28/14		1088 rec'vd	Comes with EL-PS0018

Tools	TL-HD0046	Pro Dental Pick, 5 3/4 in			Image Supply Service, Inc.	(DP-19) M S V	1	ea	1.87	1.87	1000	PO4563	09/22/14	10/01/14	1500 rec'vd			First 1500 units shipping 9/23/2014 the remaining 525 units will ship 10/23/2014

Electronic	PC-AS0019	Full Graphic Smart LCD Controller			reprapdiscount		1	ea	$28.000	$28.00	1000	PO04213			1010 rec'vd	RFQ sent 8/28
Accessories	EL-MS0119	SD card from GLCD kit			reprapdiscount		1	ea			1000	PO04213			1050 rec'vd	Comes with GLCD

Tools	TL-HD0049	6'' Deluxe Bent Stainless Steel Tweezer with Serrated Teeth			Roeder Industries	TWE6	1	ea	$2.250	$2.25	1000	PO04214	10/01/14	10/13/14	OK			It was written but not confirmed back 8/19/2014 – order not placed until 10/1/2014 when I caught that it hadn't processed. Hoping the supplier will have a short lead time. TS
										0
Accessories	SH-BX0032	30x24x13 CUSTOM BOX			Shippers Supply		1	ea	$4.770	$4.14	1000	PO04549	09/25/14		Steven
Accessories	SH-BX0025	10x8x2-1/2 32 Ect B Brown Roll End Tuck Mailer, Custom Box			Shippers Supply		1	ea	$0.980	$0.41	1000	PO04549	09/25/14		Steven
Accessories	SH-PA0030	Fabricated Foam Insert: 2 End Caps, Tray w/Plastic Corrugated & Plain Pad, v4			Shippers Supply		1	ea	$37.95	$37.95	1000	PO04549	09/25/14		Steven	Need to confirm price. $32.39 is listed for qty 1,000 in ERP
Accessories	SH-PG0056	Kraft packing tape, tan, 3x450', gummed			Shippers Supply		4267	mm	$0.000	$0.20	4267000				Steven	4 (3.1) cases of 10x rolls of 450'
Accessories	SH-PA0025	CUSTOM PAD 4-1/2X9-38			Shippers Supply		1	ea	$0.250	$0.16	1000	PO04549	09/25/14		Steven

Electronic	EL-MT0001	NEMA 17 Stepper Motors, wires cut to 60mm			Changzhou FTX Motors Co., Ltd.	SY42STH47-1504A	5	ea	$7.500	$37.50	5000	PO03814	07/22/14		10750-rec'vd 10/01	Sea shipment

Tools	TL-MS0001	Tool Kit Bag w/ LulzBot logo			Specialty incentives Inc.		1	ea	$12.500	$12.50	1000	PO04215	08/28/14		1010 rec'vd	“They do have stock at this moment”

Hardware	HD-MS0062	Metric Aluminum Unthreaded Spacer, 8MM OD, 8MM Length, M5 Screw Size			Fastenal	11485208	1	ea	$0.169	$0.17	1000	PO04498	09/17/14	See Notes	1050 rec'vd
Hardware	HD-BT0053	18-8 SS Flat Head Phillips Machine Screw Black-Oxide Finish, 4-40 Thread, 1/4" Length			Timberline	NS3420-2208/BO	20	ea	$0.027	$0.53	20000	PO04552	09/19/14	10/02/14	20000 rec'vd		1	PO04672 issued 10/7/2014 will have the remaining units with an overage of ~1000 units by 10/14/2014. -TS
Hardware	HD-BT0054	Metric Class 12.9 Socket Head Cap Screw Alloy STL, M2.5 Thread, 12mm Length, 0.45mm Pitch			Fastenal		4	ea	$0.023	$0.09	4000	PO04498	09/17/14	09/26/14	4100-9/22		1	McMaster-Carr Supply Company
Hardware	HD-WA0013	DIN 125 Zinc-Plated Class 4 Steel Flat Washer M2.5 Screw Size, 6mm OD, .45mm-.55mm Thick			Timberline	MNTR-M312.521	4	ea	$0.003	$0.01	4000	PO04552	09/19/14	09/30/14	4000 rec'vd		1	McMaster-Carr Supply Company
Hardware	PP-MP0066	Metric Brass Heat-Set Insert for Plastics, Tapered, M2-.4 Internal Thread, 2.9MM Length			McMaster-Carr Supply Company	94180A307	4	ea	$0.103	$0.41	4000	PO04574	09/23/14	09/26/14	4100 rec'vd		1
Hardware	HD-BT0107	Metric Class 12.9 Socket Head Cap Screw Alloy Steel, Black, M2 Thread, 10mm Length, 0.4mm Pitch			Fastenal		6	ea	$0.022	$0.13	6000	PO04498	09/17/14	09/26/14	18,200-9/22		1	369 in 2 week
Hardware	HD-WA0012	Steel Flat Washer, DIN 125 zinc-plated class 4,M2 screw sz, 5mm OD, .25mm-.35mm thick		40350	Fastenal	40350	6	ea	$0.002	$0.01	6000	PO04498	09/17/14	09/26/14	6000-9/22		1	McMaster-Carr Supply Company
Hardware	HD-MS0030	M3-.5 3.8mm Heatset Insert		11125995	Fastenal	11125995	69	ea	$0.060	$4.11	69000	PO04498	09/17/14	See Notes	48000 rec'vd	55k units shipping immediately / balance has a projected ETA of Dec. 5th Rep is getting these direct from the manufacturer (55k units gives us roughly 9 weeks of build, the BO should drop before then.)	1	McMasterCarr - 94180A331 As of 09/17/2014 they have a 2 week lead time on this part. I don't want to fill in because Fastenal Rep is hoping to get units from the Manufacturer sooner, just can't promise
Hardware	HD-MS0060	M5-.8 11mm Heatset Insert			Fastenal		15	ea	$0.160	$2.39	15000	PO04498	09/17/14	09/26/14	15100 rec'vd		1	McMasterCarr
Hardware	HD-MS0158	M5-.8 6.7mm Heatset Insert		11125997	Fastenal	11125997	6	ea	$0.149	$0.90	6000	PO04498	09/17/14	See Notes	16100 rec'vd	18k units shipping asap / Balance ETA 12/5		McMasterCarr -94180A361 As of 09/17/2014 they have a 2 week lead time on this part. I don't want to fill in because Fastenal Rep is hoping to get units from the Manufacturer sooner, just can't promise / Over ordered units, we should only keep 23000, and cancel the remaining 51,100 pcs.
Hardware	HD-NT0004	M3 Nut, Zinc Plated			McMaster-Carr Supply Company	90591A121	16	ea	$0.014	$0.22	16000	PO04574	09/23/14	09/26/14	2100 rec'vd		1	PO04672 Timberline order 10/7 ETA on 14K units = 10/14. -TS
Hardware	HD-BT0012	M3 Set Screw (Grub Screw)			Timberline	NS0310-0306/met	11	ea	$0.017	$0.18	11000	PO04552	09/19/14	09/30/14	11000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-WA0001	M3 Washer, Steel, Zinc Plated			Timberline	MTR-M3100321	106	ea	$0.002	$0.18	106000	PO04552	09/19/14	09/30/14	106000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-BT0044	M3 x 5 Bolt, SHCS Black-Oxide			Fastenal	39501	4	ea	$0.022	$0.09	4000	PO04498	09/17/14	09/26/14	4100-9/22		1	McMaster-Carr Supply Company
Hardware	HD-BT0039	M3 x 12 Bolt, SHCS Black-Oxide			Timberline	8050-0312	105	ea	$0.012	$1.23	105000	PO04552	09/19/14	10/02/14	152000		1	McMaster-Carr Supply Company
Hardware	HD-BT0041	M3 x 25 Bolt, SHCS Black-Oxide			Timberline	8050-0325	5	ea	$0.025	$0.13	5000	PO04552	09/19/14	10/02/14	5000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-NT0011	M4 Nut,Zinc-Plated Steel			Timberline	8100-0040	4	ea	$0.005	$0.02	4000	PO04552	09/19/14	10/02/14	4000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-NT0007	Metric Zinc-Plated Class 5 Steel Wing Nut M4 Screw Size, 0.7mm Pitch		90671	Fastenal	90671	4	ea	$0.419	$1.68	4000	PO04498	09/17/14	09/26/14	4100-9/22		1	Mcmaster-Carr Supply Company
Hardware	HD-WA0005	M4 Washer			Timberline	8200-0040	6	ea	$0.003	$0.02	6000	PO04552	09/19/14	09/30/14	6000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-BT0010	M4 x 20 Bolt, SHCS Black-Oxide	1139527	1139527	Fastenal	1139527	2	ea	$0.138	$0.28	2000	PO04498	09/17/14	09/22/14	2100-9/22		1	McMaster-Carr Supply Company
Hardware	HD-BT0030	Metric 8.8 Zinc-Pltd Steel Hex Head Cap Screw M4 Size, 20mm Length, .7mm Pitch, Fully Threaded			Timberline	8000-0420	4	ea	$0.023	$0.09	4000	PO04552	09/19/14	10/02/14	4100 rec'vd		1	Mcmaster-Carr Supply Company
Hardware	HD-BT0052	M4 x 55 Bolt, SHCS Black-Oxide			Timberline	NS8050-0455	2	ea	$0.078	$0.16	2000	PO04552	09/19/14	10/02/14	2000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-WA0007	M5 Washer, Steel, Zinc Plated			Timberline	8200-0050	109	ea	$0.003	$0.33	109000	PO04552	09/19/14	09/30/14	109000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-BT0055	Class 10.9 STL Button Head Socket Cap Screw M5 Size, 8 mm Length, .8 mm Pitch			McMaster-Carr Supply Company	91239A222	4	ea	$0.110	$0.44	4000	PO04574	09/23/14	09/26/14	4000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-BT0048	M5 x 10 Bolt, SHCS Black-Oxide			Timberline	8050-0510	106	ea	$0.021	$2.23	106000	PO04552	09/19/14	10/02/14	106200 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-BT0049	M5 x 14 Bolt, SHCS Black_Oxide			Timberline	NOR-M60051014SO	12	ea	$0.025	$0.30	12000	PO04552	09/19/14	10/02/14	12000 rec'vd		1	Mcmaster-Carr Supply Company
Hardware	HD-NT0002	M8 Nyloc Nut, Zinc Plated			Timberline	GBO-986270004	3	ea	$0.055	$0.16	3000	PO04552	09/19/14	09/30/14	3000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-WA0006	M8 Washer, Steel, Zinc Plated			Timberline	8200-0080	9	ea	$0.012	$0.11	9000	PO04552	09/19/14	09/30/14	9000 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-BT0059	M8 x 35 Bolt, BHCS Black-oxide			Timberline	NS8052-0835	2	ea	$0.073	$0.15	2000	PO04552	09/19/14	10/02/14	2100 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-WA0008	Metric Spring Steel Shim - DIN 988 0.5mm Thick, 8mm ID, 14mm OD			McMaster-Carr Supply Company	98055A114	1	ea	$0.050	$0.05	1000	PO04574	09/23/14	09/26/14	1100 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-WA0009	Metric Spring Steel Shim - DIN 988 1.0mm Thick, 8mm ID, 14mm OD			McMaster-Carr Supply Company	98055A115	1	ea	$0.060	$0.06	1000	PO04574	09/23/14	09/26/14	1050 rec'vd		1	McMaster-Carr Supply Company
Hardware	HD-MS0031	Thumb Screw Knob for M4 SHCS, Black			McMaster-Carr Supply Company	91175A062	2	ea	$0.095	$0.19	2000	PO04574	09/23/14	09/26/14	2050		1	McMaster-Carr Supply Company
Hardware	HD-MS0055	Thumb Screw Knob for M5 SHCS, Black			McMaster-Carr Supply Company	91175A063	4	ea	$0.107	$0.43	4000	PO04574	09/23/14	09/26/14	4000		1	McMaster-Carr Supply Company
Hardware	HD-MS0058	Wire Tie, 8"			Timberline	AEH#02-00-818-UVB	23	ea	$0.023	$0.53	23000	PO04552	09/19/14	10/02/14	21000 rec'vd		1	McMaster-Carr Supply Company

Accessories	SH-PG0069	3M 8898 Economy Strapping Tape - 1⁄2" x 60 yards			Uline	S-16075	700	mm	$0.000	$0.09	700000	PO04219	10/06/14	10/08/14		766 total yards needed		UoM is in mm
Accessories	SH-PG0072	3M 8898 Economy Strapping Tape - 2" x 60 yards			Uline	S-16076	600	mm	$0.001	$0.50	600000	PO04219	10/06/14	10/08/14		656 total yards needed		UoM is in mm
Tools	TL-MS0018	HDPE, 8 oz. Natural Large Round Wide-Mouth Jars			Uline	S-18070	1	ea	$0.580	$0.58	1000	PO04219	10/06/14	10/08/14
Tools	DC-LB0005	2 x 2" D.O.T. Labels - "Right to Know"			Uline	S-2845	1	ea	$0.032	$0.03	1000	PO04219	10/06/14	10/08/14				Comes in pkg, 500
Accessories	DC-LB0023	Circle Inventory Control Labels - "QC Passed"			Uline	S-13118	1	ea	$0.036	$0.04	1000	PO04244?				Did this PO include ironwood?		Comes in roll of 500
Accessories	DC-LB0021	Circle Inventory Control Labels - "Inspected by ____"			Uline	S-13119	1	ea	$0.036	$0.04	1000	PO04244?				Did this PO include ironwood?		Comes in roll of 500
Accessories	SH-PG0031	Anti-Static Control Products 2X3 STATIC SHLD BAG W/ZIP TOP			Uline	S-6509	1	ea	$0.130	$0.13	1000

Electronic	PC-BD0045	RAMBO Electronics v1.3L	UltiMachine		UltiMachine		1	ea	$78.000	$78.00	1000	PO04221	09/05/14		300	RFQ sent 8/28-Shipping 10/02 FedEx	10	10 Production RAMBos have gone to the store for RMA

Mechanical	HD-MS0204	100 Sealed Skateboard/inline/Rollerblade Skate Bearing Ball Bearings			vxb.com	kit708	11	ea	$0.200	$2.20	11000	PO04354	09/03/14	09/15/14	1100 rec'vd	RFQ sent 8/28		Comes in pkg, 100. Order qty is 110 ?

Tools	TL-HD0009	7 1/2" Nylon Handle Clam Knife			WEBstaurant Store	35340592	1	ea	$2.030	$2.03	1000	PO04413	09/11/14	09/26/14	1351-9/23	Shipping 09/26/2014

																Good to order

																Actual inventory/receiving notes – Mary