## Sheet1
		Schedule – Product Development Cycle
		03-02	03-09	03-16	03-23	03-30	04-06	05-18	05-25	06-01	06-08	06-15	06-22	06-29	07-06	07-13	07-20	07-27	08-03	08-10	08-17	08-24
							Basic proof of concept prototypes for all major projects					Build up 5 prototypes for performance testing / RBF cycles					Build 5 “final” prototypes for verificatioon
TASKS	OWNER						EVT / Engineering Verification Test
R&D – Mechanical
Make change list	Seth
Finish Design for EVT	Brent / Julie
Test Belt drive Z	Brent
Parallel Path z-screw drive	Brent
Test v-slot &other	Brent
Integrated control box design	Julie / Chris
Sheet metal design	Julie / Brent
Basic design configuration lock (drive type of all axes, auto leveling sequence)	All
Autoleveling prototyping	Patrick
Autoleveling LTT	Julie / Patrick
Redesign attaching mechanism for the bed	Brent
LCD workflow redesign	Patrick
Different heatsink fan	Brent

Performance / mechanical testing	Brent

First batch sheet metal	Brent / Julie
Final batch sheet metal	Brent / Julie
first batch IM parts (order → test)	Julie
final IM parts (order → test)	Julie
Make drawing for Avon mechanical
Make EVT BOM	Brent
Finalize BOM for DVT	Brnet / Seth
EMI testing	Chris
Finalize BOM for SAT
Get product specs to Marketing	Brent
R&D Electrical
Feature list for Avon
Connector list for Avon
New Avon layout
Design spin for any changes to board for DVT
LCD board layout
Lights
LCD menu structure
Wi-Fi module
Thermal fuse
Firmware
Software
Cura profiles
Any needed Cura changes
Build & Test
Built and test EVT printers
Test new boards
EMC test Printer with EVT Avon
EMC test with EVT printer
Final EMC testing on Production printer
Test bed leveling on TAZ
Test final firmware/software configuration
Packaging / Documentation
Foam design
Packaging Design
User Manual
Documentation
Procurement
Camellia (DVT/SAT) Parts
Production Parts – Long lead
Order boards as many times as we need
Order parts for EVT Printers
Order parts for 20 DVT Printers
Order production samples of Boards
Order long lead production parts
Order short lead production parts
Plastic Parts
Manufacturing
Process step define (presub-FA)		1st pass
Process step layout
Assembly line layout & BOM
Mfg line 2 construction/ purchase
Resource Plan proposal/ approval
Recruiting mfg staffs
Training new team
Build 20 of the DVT printers
Build 30 of th SAT printers
Design/Build up any fixturing needs for Assembly
Build production
Assembly OHAI Kits
PreSub Op setup & production prep
Cycle time modeling		1st pass
Presub/Sub Test Defined
Pre/Sub Test Equip Des/Setup
- Harness Test Fixture
- Other fixtures
MO
Marketing / PR / Sales / CS
Final Product Photos
Product Pages
Customer support training
Product Description
Product name
EVT laser etch concept
Printers for review
Product name for new board