## Sheet1
Lancewood Changes			Details	Responsible	Est time to completion	Confidence level
Integrated electronics
	Internal PS	Yes	Meanwell 500W – Switch mounting in case for the 500W	Bam		Integrate Internal Power Supply
	Integrated LCD	Yes	Same LCD – possible better grounding	Bam
	LCD workflow	Yes	One more round with marketing	Patrick
	Move Plugs to back	Yes		Julie
	FCC/CE	Yes	Class A with RAMBo, test for B?	Seth

Auto-leveling		Yes	Testing In progress	Patrick
	Better wiper / lower	Maybe	Currently testing Nylon scrubber pad material	Patrick

Mechanical redesign
	Dual Extrusion Fans	Yes	We just need to make sure splicing the fans together is a good way to go here	Bam
	Stainless Drive rods	Yes	Sticking with Misumi, will test SST and coated in 1st round prototypes	Bam
	Min and Max switches (z)	Yes	Y and X yes, maybe on Z	Julie
	Stiffer Axis for droop/bed warp	Yes	12mm x-rods, possible firmware compensation	Bam
	Tighter tolerance bushings	Maybe	Testing In progress	Bam
	New Drive system in Z (IM)	Maybe	IM parts in progress, Need to test to justify 2nd Z rod. Printed parts will backup in case of IM parts not being ready in time	Julie
	Filament cleaner/wiper	Yes	Currently testing foam version	Seth
	Easier to assemble Y axis	Yes	In testing	Bam
	Shippable mounted toolhead	Maybe	If secure enough, need to test	Bam
	Aluminum frame connectors	Yes		Bam
	Remove Name Plate	Yes		Bam
	Remove all Switch arms	Yes		Bam

Injection molded parts		Yes	y axis bearing holder, Z lowers and uppers, x ends	Julie

Marketing				Harris
	New Box	Yes	Something more conducive to retail shelving	Harris
	New Name	Yes	TAZ 6	Harris
	New document package	Yes		Harris
	New Laser etching on Case	Yes		Ben

Easier to Assemble for customer		Yes	30 min box to print?
Less expensive		Yes
Easier to Assemble for manufacturing		Yes

## Sheet2
PP Listing		IM / Printed / machined	Assigned	Changing?	Notes	Percent Done
X axis
	Xend idler	IM	Julie	yes		30.00%
	X-end Idler backup	Printed +Sheet metal	bam	yes		30.00%
	X-end motor	IM	Julie	yes		30.00%
	X-end motor backup	Printed +Sheet metal	bam	yes		30.00%
	X-bearing holder(s)	Printed	bam	yes		30.00%
	X-carriage	Sheet metal	bam	yes		50.00%
	belt mount	Printed	bam	yes	Need to redraw in FreeCAD, thru holes instead of inserts	0.00%

Y axis
	Y-attachment	Printed	bam	yes	2 designed paths, need to choose between	95.00%
	Y-corners	IM	Julie	yes		90.00%
	Y-idler	Printed	---	no	Just needs FreeCAD redraw	75.00%
	Y-motor	Printed	---	no	Just needs FreeCAD redraw	75.00%
	Bed bearing holder	IM	Julie	Yes		90.00%
	Bed corner	Printed	bam	No		90.00%
	Belt / switch mount	Printed	bam	yes	redrawn, testing	95.00%
	Y-harness connection	Printed	bam	yes	Integrated into belt mount	95.00%

Z axis
	Z lowers	IM	Julie	Yes		50.00%
	Z-uppers	IM	Julie	Yes		50.00%
	Z min switch mounting	IM	Julie	Yes	Part of Z lower	30.00%
	Z-max switch mounting	IM	Julie	Yes	Part of x-end idler	30.00%

Printhead
	HB Gears	Printed	bam	maybe	Testing different materials, model will remain the same	90.00%
	Extruder body	Printed		no	Use current design	100.00%
	Extruder Latch	Printed		no	Use current design	100.00%
	Extruder mount	Printed	bam	yes	Redraw in freecad	30.00%
	Fan shrouds	Printed	bam	yes	Redraw in Freecad	0.00%
	Switch mounting	Printed	bam	yes	Part of extruder mount	0.00%

Sheet metal
	Left side	Sheet Metal	Julie	yes		20.00%
	Right Side	Sheet Metal	Julie	yes		20.00%
	Control box	Sheet Metal	Julie	yes		30.00%
	Bed Plate	Sheet Metal	Julie	yes		50.00%
	Y-motor plate	Sheet Metal	Julie	yes	Changing per marketing's request	50.00%
	Y-idler plate	Sheet Metal	Julie	yes	Changing per marketing's request	50.00%

Misc
	Wiper mount	Printed	bam	Maybe	Keep as is on the mini until machines are built up for testing	50.00%
	Nameplate	??	bam	Maybe		0.00%
	Control Box mounting	Printed	bam	No	Need to redraw in FreeCAD	50.00%
	Spool Arm	Printed		yes	Need to redraw in FreeCAD, make less sharp	0.00%
	Feed tube holder	Printed		yes	Need to redraw in FreeCAD, make less sharp	0.00%
	Feed tube spinner	Printed		No	Keep the same as it is currently	100.00%
	Filament cleaning system	???	Bam / Seth	Yes	Need concept design	0.00%

Sourcing
	Control box fan		bam	yes	Need to source UL, waiting on pelonis	30.00%
	Extrusion fan		bam	yes	Need to source UL, waiting on pelonis	30.00%
	Heatsink fan		bam	Maybe	Need to source UL, waiting on pelonis	30.00%
	Switch		Seth	Maybe	Change color? Probably not, green looks cool though	100.00%

## Sheet3
Cleaner/easier wiring	Yes	make wire harnesses easier to build. Don't combine multiple into one if possible	Bam
Quieter fans	Maybe	quieter UL fans ordered, will test when delivered	Bam
Cable guides	Yes	Larger may be necessary, still need to solve y-axis	Bam
revised Extruder	Maybe	Something without spring screws and a significantly easier latch	Bam
Sheet metal sides / ctrl box	Yes	Need to design sheet metal sides and control box	Julie
Z-Backup switches	Yes	We have the switches, still in testing	Chris
No LCD back-power	Yes	In progress with the new board testing	Chris
New Board	Yes	New layout is needed after FCC testing	Chris
get mktg. Approval on case	Yes	Make up rendering / mockup of control box to get mktg approval	Julie
reset switch on front	Maybe	Need to check with marketing and source	Chris
esd changes – rrd	Maybe	Chris will get in touch with rrd about esd changes	Chris