## Sheet1
Unresolved Lancewood design changes

System	Description	Responsible	Priority	ETA	Notes
Print-Head	Verify current mount in drop test	Bam	2
	redraw fans in freecad	Bam	1
	redraw x-car	Bam	2
	verify that 16 pin connector will not cause compatibility issues	Bam	2
	finalize switch location (drives x-ends)	Julie	4
	redraw bearing holders to have tighter fit	Bam	2

Electronics	finish firmware	Patrick	4
	prototype molex harness	Patrick	5
	verify current control box mounting – redesign if necessary	Julie	2

Z/X axes	design in switch mounting (x-min,x-max,z-max)	Julie	3
	Prototype single rod setup and make decision	Julie	5
	-SST vs black rods - comparatively test in system	Bam	1

Y-assembly	New switch – can not melt even with custom firmware	Bam	4
	redraw bed plate	Bam	3
	finalize connector	Bam	2		10 pin molex+std bed connector
	order IM and verify	Julie	4
	try out different thumb screw caps	Bam	1
	test all units with new wiper – need confidence by 9/11	Patrick	4		branched out into separate project

Frame	Verify minimum x-axis length (500mm goal)	Julie	2
	Quote sheet metal corner brackets	Bam	4		Redrawn and out for quote 9/1

Misc	Complete BOM	Bam	4