## Sheet1
	EasyTAZ Mini – Product Development Cycle
	03-24	03-31	04-07	04-14	04-21	04-28	05-05	05-12	05-19	05-26	06-02	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08
Wdays to Launch	109 days left			94				74			59			44				24			9		0
	EVT - Engineering Validation Test					DVT - Design Verification Test					DMT/SAT – Des Maturity/ Ship Apprv Test					Production
	Design Validation – Functionally focused					Verification – Reliability focused – RBF cycles					Qualification – MFG/ Quality/ Shippability
		(5 machines)					(10 machines)					(30 machines)

	3/24	Frame Design Decision: Cube or Mini_TAZ?				4/28	EVT Testing commences					7/28	Risk decision to place orders 200? prod units

						6/16	Review & Risk SAT Entry approval, allow ordering parts for 30 SAT mach's					7/28	Finalize Packaging

	3/24	Electronics Design Decision: Thumbs up to current plan				4/28	Design Config LOCKED					SA	Review & Ship Approved

						5/05	Review & Risk DVT Entry approval: to order parts for >10 DVT machines

	Items to Validate:					# of machine			Items to Verify:					# of machine		Items to Verify:				# of machine
	1)	Printability					5			1) Performance(speed,...)					10		1) Manufacturability				30
	2)	Repeatability					use above			2) Repeatability/Reliability					use above		2) Longterm Reliability				same
	3)	Userablity					use above			3) Userability					use above
	4)	Mechanical Spec					use above			4) Environmental					3
	5)	Electrical spec					use above			5) Op Shock					3
						6) Non-Opshock					use above
						7) EMC/FCC					3
	Type of Test					Type of Test					How long?		Type of Test				How long?
	1)	Can it print as well as Guava					1) Print-Visual/Time measure					1) Long term reliability				72	hr
	2)	Is bed leveling working					2) Short print/Cal, 24hr print					24	hr	2) Assembly test run
	3)	Frame Stiffness					3) Hot, Hot/wet, Cold					3	hr/ea
	4)	Basic Electronics Function					4) Bump test
	5)					5) Drop test
						6) Near/far field test & FCC
	Test Acceptance or Pass/Fail Criteria					Test Acceptance or Pass/Fail Criteria					Test Acceptance or Pass/Fail Criteria
	1)					1)					1) E.g, No Calibration drift, visual/
	2)					2)					Measurement, dimension accuracy,
	3)					3)					consistency, visual printing quality
	4)					4)
	5)					5)
						6)

	Rules:	- Design changes allowed - No architect-related changes after					- Minor changes/improvements from RBF					- MFG and “Ship” config hence NO change
		config “locked” date unless program risk (schedule, cost, …) studied					cycles allowed - No design config/architect-related					unless last minute discovery renders
		& approved by the Project Approval Committee (PAC-stakeholders)					changes allowed unless approved by PAC					the machine not shippable, req PAC apprv.

	PAC		Seth:
	Signed Off		Steven:
			Chris:
			Jeff: