## Sheet1
Easy TAZ Mini - Work Breakdown Schedule _ v. 3.0
				06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01
				92					49					20				0
TASKS		OWNER	MAN Hrs	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-					SAT–Design Maturity / Ship Approval Test / –Daffodil-				Production Commences & Inventory Buildup			Product Announcement & Sales start			Cyber Monday
Architect		Seth
Cube or Lulzbot? Decision		Seth
- CAD		Seth
- Build mockups		Seth
- Cost estimate		Seth/ Chris
Electronics- Controller & Comm		TBD
- Research features		Aaron
- Research Market trends		Aaron
- Pros & Cons on FW effort		Aaron
- Final Config/feature proposal		Seth
- Final Config Decision		All
Non-UL/UL Ready/ Full UL?		Seth & All
- Define what need to be done		Seth/ Chris
- Re cost estimate		Seth
Software		Aaron/ Jeff
UI Flow		Aaron/Jeff					<<<
UI Design		Steven
Kernel		Jeff					<<<
uBoot		Jeff					<<<
SD Image		Jeff					<<<
Package Slic3r,Octoprint,Custom		Aaron/Jeff
USB drive automount		Aaron/Jeff
Wifi		Aaron/Jeff
LED driver		Aaron/Jeff
Octo Web Daemon		Jeff
Slicing		Jeff/Sound
Slicing ini's		Brent
Octoprint UI		Aaron
Firmware
RAMBO – SD		Aaron/Seth					no longer applied
RAMBO – BBB		Aaron/Seth
RAMBO – EZT HW		Aaron/Seth
Auto Leveling		Aaron/Seth
Code Release		Aaron/Jeff					DVT					SAT
Video Production
Mechanical		Seth
Frame		Seth					<<<
X-Axis		Seth					<<<
Y-Axis		Seth					<<<
Z-Axis		Seth					<<<
Extruder		Seth/ Brent					<<<
Drive System		Seth					<<<
New Spool loc/feed		Seth
LCD Mount		Seth/ Aaron					<<<
Motor Selection		Seth
Nozzle Sel/ Design		Seth/ Brent					<<<
Heat bed		Seth/ Brent					<<<
- PET tape?
- Holding the bed?
Auto Bed Leveling		Seth/ Brent
Electronics/ Electrical		Seth
Mini-RAMBO		Chris
LCD		Seth/ Aaron
Baseboard		Aaron/ LkSp					Des Comp		Samples
Wiring (HW vs Conn)		Seth/ Chris
Power Supply		Seth/ Chris
Lights/LEDs		Seth
Grd/ EMI Shielding		Seth/ Chris
Camera		Seth					<<<
USB		Seth & All					<<<
Switches		Seth
Breadboard Testing		Seth

				06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01
				92					49					20				0
TASKS		OWNER	MAN Hrs	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-					SAT–Design Maturity / Ship Approval Test / –Daffodil-				Production Commences & Inventory Buildup			Product Announcement & Sales start			Cyber Monday
Build & Test		Seth
Build Prototypes/ Test machines		Seth/ Chris
Functional		Seth/ Brent
Speed		Seth/ Brent
Mechanical Performance		Seth/ Brent
Useability		Seth/ Chris
Environmental		Seth/ Brent
Op-Shock		Seth/ Brent
Non-Opshock		Seth/ Brent
EMC		Seth/ Chris
Long Term Reliability		Seth/ Brent
Packaging/ Documentation		Steven
Frame available for prototype		Seth
Shipping Foam		Steven					1st Pro
Fed-EX Test		Steven					FedEx
Unbox Manual		Steven
Operation Manual		Steven
Consumer's Open Box Exp Test		Steven
Print Profiles		Seth
BOM Creation		Seth
Procurement		Seth/ Chris
DVT Parts		Seth
SAT		Seth
Production		Seth/ Chris
Risk Purchases Long Lead Items		Seth/ Chris					<<<	7/22
Plastic		Chris/ Stan
Manufacturing		Chris
Process step define (presub-FA)		Seth/ Chris
Process step layout		Chris
Assembly line layout & BOM		Chris
Mfg line 2 construction/ purchase		Andy/ Chris
Resource Plan proposal/ approval		Chris/ Jeff
Recruiting mfg staffs		Chris
Training new team		Chris
Build SAT machines		Chris
Assembly OHAI Kits		Seth/Robert
PreSubs		Chris
Cycle time modeling		Chris
Cycle time verification		Chris
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris
Pre/Sub Test Equip Des/Setup		Chris
OpenERP Routing		Chris
Marketing / PR		Harris
Product Design (Expanded)		All					>>>
Business Case		Harris					<<<
Brand / Competitive Analysis		Harris					<<<
Goal(s) Articulation		Harris					<<<
Strategic Comms. Framework		Harris					<<<
Target Audience Identification		Harris					<<<
Creative Brief		All					<<<
Graphic Approach - Packaging		Harris/Steven					<<<
Product Naming		All					<<<
Strategic Message Development		All					<<<
High-Level Tactical Plan		Harris/Rachael					<<<
Product Collateral Design		Harris/Steven					<<<
Website-Related Design Recs		Harris/Steven					<<<
Reseller Demos		Harris/Rachael