## Sheet1
			LulzBot Mini – Product Development Cycle – v3.2
			08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01	12-08	12-15

TASKS		OWNER	EVT / Engineering Verification Test / (Begonia)					DVT/SAT – Qualification / Design Verification/Ship Approval Test / (Camellia)					Production & Inventory Buildup / (Daffodil)		CYBER Monday	Production & Inventory Buildup / (Daffodil)
R&D – Mechanical		Seth
Frame- finalize design/ order DVT		Seth
Nozzle- retention		Brent
Bed Mounting – Z corner		Brent
PEI		Brent				PEI
Quik-exchange Print head design		Seth/ Brent
Drive Rod		Seth

Final BOM		Seth
R&D Electrical		Seth
Wire/cable/harness		Seth/Brent
Z-Overrun Sw		Seth
Thermal Cutoff verifiy		Brent

Software		Steven
SW package selection		Steven
Open SW		Steven
Bug testing		Steven
GUI changes		Steven
Print Profiles		Brent/Steven

Code Release		Steven						DVT/SAT				Production
Build & Test		Seth
Test Plan		Seth/ Chris
Build Prototypes/ Test machines		Seth/ Brent
Functional		Seth/ Brent
Speed		Seth/ Brent
Mechanical Performance		Seth/ Brent
Useability		Seth/ Steven
Environmental		Seth/ Brent
Op-Shock		Seth/ Brent
Non-Opshock		Seth/ Brent
EMC		Seth
Long Term Reliability		Seth/ Stan
Packaging/ Documentation		Steven
Machine for foam prototype		Seth
Shipping Foam		Steven
Final Foam design verify		Steven
Internal Drop Test
Fed-EX Test		Steven
Operation Manual		Steven
- 16-Page PDF otr Fold-out Poster		Steven
Consumer's Open Box Exp Test		Steven
Procurement
Camellia (DVT/SAT) Parts		Seth/ Toni
Production Parts – Long lead		Seth/ Jeff
Production Parts		Toni
Plastic		Chris/ Stan
Manufacturing		Chris
Process step define (presub-FA)		Seth/ Chris	1st pass
Process step layout		Chris
Assembly line layout & BOM		Chris
Mfg line 2 construction/ purchase		Andy/ Chris
Resource Plan proposal/ approval		Chris/ Jeff
Recruiting mfg staffs		Chris
Training new team		Chris
Build DVT/SAT Camellia machines		Chris
Assembly OHAI Kits		Seth/Robert
PreSub Op setup & production prep		Chris
Cycle time modeling		Chris	1st pass
Cycle time verification		Chris
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris
Pre/Sub Test Equip Des/Setup		Chris
- Harness Test Fixture		Brent
OpenERP Routing		Chris
Marketing / PR		Harris
Frame Design		Natasha/Kevin
Customer Survey		Harris
Market Research Review		Harris
Product Packaging		Natasha/Kevin
Reseller Preview		Harris/Natasha
Reseller Engagement		Rachael/Ben
Product Photos		Kevin
Product Collateral Design		Harris
Product Description		Harris
Press Prioritization		Harris/Schwartz
Press Engagement		Harris/Schwartz